Planning Timeline

6 October 2025: ToC Tool open for 2025 ToC updates 17 October 2025: ToC Tool close for 2025 ToC updates 20 October 2025: ToC Tool open for 2026 ToC updates 25 October 2025: 2026/27 Program/ Accelerator envelopes endorsed by GST 31 October 2025: 2026/27 Program/ Accelerator envelopes endorsed by GLT 01 November 2025: Launch of the Planning Module 14 November 2025: Proposed 2026/27 PORBs submitted for internal reviews & quality assurance based on (i) GLT-endorsed Prog./ Accelerator envelopes; and (ii) Program/ Accelerator-level prioritization 14 November 2025: ToC Tool close for 2026 ToC updates 21 November 2025: Proposed 2026—27 PORBs submitted for GST review and endorsement 28 November 2025: 2026—27 PORBs endorsed by the GST subject to SC approval of W1/2 Budget 5 December 2025: 2026—27 PORBs endorsed by the GLT subject to SC approval of W1/2 Budget 12 December 2025: 2026—27 Prog./ Accelerator Plans of Results and Budgets (PORB) approved by EMD following SC approval of W1/2 Budget